## SCH
PROJECT PLANNING SCHEDULE :
PROJECT: 2025 EEE SEABOAT
| No. of Wks / days | Plan / Actual | 2024-05-05 |  |  |  |  | 2024-05-12 |  |  |  |  | 2024-05-19 |  |  |  |  | 2024-05-26 |  |  |  |  | 2024-06-02 |  |  |  |  | 2024-06-09 |  |  |  |  | 2024-06-16 |  |  |  |  | 2024-02-26 |  |  |  |  | 2024-03-04 |  |  |  |  | Notes:
|  |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 23 |  |  |  |  | 24 |  |  |  |  | - Project length is 7 weeks
[12 empty] | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 9
|  |  | m | t | w | t | f | m | t | w | t | f | m | t | w | t | f | m | t | w | t | f | m | t | w | t | f | m | t | w | t | f | m | t | w | t | f | m | t | w | t | f | m | t | w | t | f | - One week buffer is given under final testing and arrangement' section
INTRODUCTION AND WORKSHOPS | [47 empty] | - Stage 1 specialisation includes:
Project Introduction | 1 day | Actual | [46 empty] | IR + Radio sensing | bar: f
Introduction to Professional Competencies | 1 day | Actual | [46 empty] | Ultrasonic communications | bar: f
Teamwork | 1 day | Actual | [46 empty] | Controlling the rover (Software) | bar: m
Project Management | 1 day | Actual | [45 empty] | - Stage 2 specialisation includes: | bar: t
Ethics in Engineering | 1 day | Actual | [46 empty] | Magnetic sensing | bar: 2 w
Academic Writing and Technical Communication | 1 day | Actual | [46 empty] | Complete Power System | bar: 2 t
Report Formative Feedback Session | 1 day | Actual | [45 empty] | - Add in comments for dates that we meet up with staff members | bar: 5 m
DELIVERABLES
Interim Presentation | 1 day | Actual | bar: 3 t
Reflections on Professional Practice | 1 day | Actual | bar: 5 t
Project Report | 1 day | Actual | bar: 5 t
Interview, Demo and Competition | 1 day | Actual | bar: 6 t
PLANNING AND PRELIMINARY
Internal Kick Off Meeting | 1 day | Actual | bar: m
Understanding the project | 1 day | Actual | bar: m
Assigning roles of group members | 1 day | Actual | bar: m
BUILDING THE PROTOTYPE
Stage 1 specialisations - Prototype concept development by assigned pairs | 3 days | Plan | bar: m to w
Stage 1 specialisations - Prototype concept review and discussion | 1 day | Plan | bar: t
Stage 1 specialisations - General design discussion | 1 day | Plan | bar: t
Stage 1 specialisations - Post discussion modification by assigned pairs | 2 days | Plan | bar: t to 2 f
Stage 2 specialisations - Prototype concept development by assigned pairs | 2 days | Plan | bar: 2 m to 2 t
Stage 2 specialisations - Prototype concept review and discussion | 1 day | Plan | bar: 2 w
Stage 2 specialisations - General design discussion | 1 day | Plan | bar: 2 w
Stage 2 specialisations - Post discussion modification by assigned pairs | 2 days | Plan | bar: 2 w to 2 t
Client's drawing review (IFC) | 1 week | Plan
Receive of APPROVED/COMMENTED Drawings (IFC) | 1 day | Plan
EQUIPMENT PROCUREMENT |  | Plan | bar: m to 5 w; 6 f to 9 f
Material preparation | 2.5 weeks | Plan | bar: m to f
Plan
COMPONENT PREPARATION & ORDERING
Listing preparation based on stage 1 specialisations - general design | 2 days | Plan | bar: t to 2 f
Order stage 1 components | 1 day | Plan | bar: 2 f
Listing preparation based on stage 2 specialisations - general design | 2 days | Plan | bar: 2 w to 2 t
Order stage 2 components | 1 day | Plan | bar: 2 t
BUILDING THE PROTOTYPE
Integration of sensors into the arduino | 1.5 weeks | Plan | bar: t to 3 f
Constructuing the robot | 2 weeks | Plan | bar: t to 3 w
Actual
TESTING & MODIFICATION
Stage 1 specialisations - Robot & Software Functionality Testing | 2 days | Plan | bar: 2 t to 2 w
Stage 1 specialisations - Post-Testing Modifications | 4 days | Plan | bar: 2 t to 3 t
Stage 1 specialisations - Post-Modifications Testing | 2 days | Plan | bar: 3 w to 3 t
Stage 2 specialisations - Robot & Software Functionality Testing | 2 days | Plan | bar: 3 t to 4 f
Stage 2 specialisations - Post-Testing Modifications | 3 days | Plan | bar: 4 m to 4 w
Stage 2 specialisations - Post-Modifications Testing | 2 days | Plan | bar: 4 t to 5 f
Final Testing and Refinement | 1 week | Plan | bar: 5 m to 6 f
DELIVERABLES PREPARATION
Conclude ideas for interim presentation | 1 day | Plan | bar: 3 w
Furnish reflections on professional practice | 2 days | Plan | bar: 5 t to 5 w
Project report preparation | 3 days | Plan | bar: 5 m to 5 w
Interview, Demo and Competition preparation | 2 days | Plan | bar: 6 f to 6 m
|  |  |  | = | Introduction/ Workshops | [7 empty] | = | Specialisations pair work | [7 empty] | = | Component ordering | [6 empty] | = | Testing
|  |  |  | = | Deliverables | [7 empty] | = | Group discussion | [7 empty] | = | Sensor integration | [6 empty] | = | Modifications
|  |  |  | = | Planning and Preliminary | [7 empty] | = | Component listing | [7 empty] | = | Robot construction | [6 empty] | = | Deliverables preparation